## Dash Board
PROJECT Work Permit Dashboard
Date:
LTI, MTC, FI, FA Trend of IHPL
Project Department Trend
Total Work Permit
Work Agency
Safety Observation
Location Incharge
Total Permit Closed
Category of permit
LOTO Authorized Person
LOTO Quantity & Closer
Suppliers Dealing
201
25
201
PPE Percentage
MTC & Project
August 9, 2024
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
38
LOTO Authorized
LOTO Energised
30
30
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
32
General Work include Electrical, Chemical, Gas line,Hot work, Load liffting and others
Project team successfully close 50 Red Zone Work Permit
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## HSE (hidden)
IHPL |  |  |  | Project |  |  |  | Date | PPE Use | Row Labels | Average of PPE Use
Accident/ Incident Report (Major) | Short Cut | 2020 | 2021 | Accident/ Incident Report (Major) | Short Cut | 2020 | 2021 | 4383100% | 100% | 2020 | 99.98%
Medical Treatment Case | MTC | 11 | 1 | Medical Treatment Case | MTC | 0 | 0 | 4386200% | 100% | 2021 | 98.13%
First Aid | FA | 64 | 68 | First Aid | FA | 0 | 0 | 4389100% | 99.88% | Grand Total | 99.06%
Lost Time Injury | LTI | 0 | 2 | Lost Time Injury | LTI | 0 | 0 | 4392200% | 100%
Fire Incident | FI | 0 | 0 | Fire Incident | FI | 0 | 0 | 4395200% | 100%
[8 empty] | 4398300% | 99.93%
[8 empty] | 4401300% | 100%
[8 empty] | 4404400% | 100%
[8 empty] | 4407500% | 100%
[8 empty] | 4410500% | 100%
[8 empty] | 4413600% | 100%
[8 empty] | 4416600% | 100%
[8 empty] | 4419700% | 100%
[8 empty] | 4422800% | 100%
[8 empty] | 4425600% | 100%
[8 empty] | 4428700% | 96.39%
[8 empty] | 4431700% | 95.51%
[8 empty] | 4434800% | 96.76%
[8 empty] | 4437800% | 97.32%
[8 empty] | 4440900% | 97.47%
[8 empty] | 4444000% | 97.86%
[8 empty] | 4447000% | 97.85%
[8 empty] | 4450100% | 99.18%
[8 empty] | 4453100% | 99.18%

## Safety Observation
Sr. No | Safety Observation | 32
1 | Rain water Harvesting Safety Basement
2 | Rain water Harvesting Electrical DB Guard
3 | 3rd floor AC leakage check through supplier
4 | Sitkiny Fixing C-Tack Plant Door lock for proper safety
5 | NMP floor epoxy work
6 | Drying chain oven Toe Guard with New extended base
7 | All duct line of Drying chain oven covered with new insulation
8 | Drying chain oven Burner motor 3D guarding
9 | Narrow platform modification for emergency movement beside Drying chain Burner
10 | Sharp edge in cable tray remove and roofing screw finishing
11 | Fixed railing beside stair in the drying chain oven loading area
12 | Safety Guard both side of the drying chain oven in different location
13 | Railing setup in different location of Drying chain oven
14 | Ram shade modification work at Unit-2
15 | Leaching tank observation closing
16 | Drying chain oven Safety guard for Cooling fan
17 | Drying chain oven electrical tray modification and repair work
18 | Unit-2 rooftop leakage repair
19 | U-2 Back side Sunshade top brick Wall Making
20 | Drying chain oven wall fan repair which makes abnormal Noise
21 | Auto Overlock 3D Guard & Interlocking System installation work
22 | Floor repairing work at U2
23 | CO2 suppression system at IT server Room
24 | Slab making work at unit-01
25 | Washing area floor repair at unit-01 ground floor
26 | Water pipe line relocation at unit-3 roof top
27 | Underground rain water tank cleaning
28 | LPS System installation
29 | Male wash room painting
30 | Worker canteen tiles repair
31 | Slab leveling work at unit-01 G/F
32 | Water line pipe clump fixing work at Unit-3

## Pivot (hidden)
Total Permit | 201 |  |  | Location incharge | 38 |  |  |  |  | Supplier | 25 |  | 201 |  | 30 |  |  | 30
Row Labels | Count of Work Permit | Row Labels | Count of Work Permit Serial No | Row Labels | Count of Work Permit | Row Labels | Count of Work Permit Serial No | Row Labels | Count of Work Permit | Row Labels | Count of Work Permit | Row Labels | Count of Work Permit | Row Labels | Count of Work Permit |  | Row Labels | Count of Work Permit
2021 | 119 | Bakkar | 69 | Arup-Project | 1 | General Work | 133 | Ali,Faruk,Kaisar | 1 | Afrin Eng. Works | 1 | 2021 | 119 | Ali,Faruk,Kaisar | 1 |  | Ali, Faruk | 1
Qtr4 | 119 | Dulal | 2 | Azim-HSE | 2 | Work at Height | 66 | Azim-HSE | 1 | Aquafit | 2 | Qtr4 | 119 | Azim-HSE | 1 |  | Azim-HSE | 1
Nov | 66 | Mahfuz | 76 | Farhad-U2 | 3 | Confined Space | 2 | Bakkar | 1 | Cosmic | 1 | Nov | 65 | Bakkar | 1 |  | Bakkar | 1
Dec | 53 | Zahirul | 7 | Helal-Admin | 1 | (blank) |  | Biplob | 1 | DCS | 42 | Dec | 54 | Biplob | 1 |  | Biplob | 1
2022 | 82 | Shamim | 45 | Imran-MTC | 2 | Grand Total | 201 | Faruk | 24 | Jahangir Mechanical work | 3 | 2022 | 82 | Faruk | 24 |  | Faruk | 24
Qtr1 | 82 | Sayeed | 2 | Jahangir-Technical | 1 |  |  | HSE | 2 | Mars Build | 19 | Qtr1 | 82 | HSE | 2 |  | HSE | 2
Jan | 82 | Grand Total | 201 | Kamal-Admin | 11 |  |  | Grand Total | 30 | Mars Build & Jinnat Ali | 1 | Jan | 82 | Grand Total | 30 |  | Grand Total | 30
Feb |  |  |  | Koushik-U1 | 11 |  |  |  |  | Mars build & Vision Engineering | 2 | Feb
Grand Total | 201 |  |  | Mahfuz-Project | 39 |  |  |  |  | Nerolack | 2 | Grand Total | 201
|  |  |  | Md.Kaisar - W/H | 1 |  |  |  |  | Popular Electronics | 2
|  |  |  | Pijush-Admin | 3 |  |  |  |  | Project Team | 48
|  |  |  | Pranab- U3 | 32 |  |  |  |  | Smart Water | 6
|  |  |  | Saiful -Admin | 1 |  |  |  |  | Vision Engineering | 18
|  |  |  | Samim-Project | 12 |  |  |  |  | Zinnat Ali Enterprise | 2
|  |  |  | Soliman-Admin | 3 |  |  |  |  | BBSL&DCS | 13
|  |  |  | Zahirul-Project | 6 |  |  |  |  | BBSL&Vision | 1
|  |  |  | Mizan-Technical | 1 |  |  |  |  | DCS&PN | 1
|  |  |  | Samim-Project | 9 |  |  |  |  | SS Weighing solution | 2
|  |  |  | Shawkat-MTC | 6 |  |  |  |  | Globe enterprise | 2
|  |  |  | Saju-Technical | 2 |  |  |  |  | MM Motors | 1
|  |  |  | kamal-WH | 5 |  |  |  |  | MBSL | 19
|  |  |  | Sohan-U2 | 7 |  |  |  |  | Solidio | 2 |  |  | Row Labels | Count of Work Permit
|  |  |  | Kazi-Packing | 2 |  |  |  |  | Talukdar | 2 |  |  | Red Zone | 50 | 50 | Project team successfully close 50 Red Zone Work Permit
|  |  |  | Mehedi-U2 | 1 |  |  |  |  | Navana | 2 |  |  | General Area | 151
|  |  |  | Kaiser-WH | 2 |  |  |  |  | Emkay | 5 |  |  | Grand Total | 201
|  |  |  | Forkan-Admin | 1 |  |  |  |  | Idea Eng. | 2
|  |  |  | Shazed-U2 | 2 |  |  |  |  | (blank)
|  |  |  | Aziz-U2 | 2 |  |  |  |  | Grand Total | 201
|  |  |  | Ashraf-WH | 2
|  |  |  | Imran-HSE | 15
|  |  |  | Tamjid-U1&3 | 1
|  |  |  | Sayeed- Project | 1
|  |  |  | Saiful-U3 | 3
|  |  |  | Shahadat-Admin | 1
|  |  |  | Dabirul-Admin | 4
|  |  |  | Sarwar-WH | 1
|  |  |  | Bakkar-Project | 3
|  |  |  | Alvi-U2 | 1
(blank)
|  |  |  | Grand Total | 201

## Raw Data
Date: | 2024-08-09
Sr. No | Work Permit Serial No | Work description | Red Zone | Permit Taken By | Supplier name/ Vendor Name | Permit Issuer | Work Agency | location Incharge | Unit | Permit Type | Category of permit | PPE Use | LOTO Authorized Person | LOTO Energised Person | LOTO Color | Permit Taken Date | Job Start Time | Permit Handover Date | Job Complete Time | Remark/ Any observation From HSE
1 | 0706 | Platform installation for rain water harvesting with drilling | General Area | Bakkar | Project Team | Akram-HSE | Bakkar | Soliman-Admin | Unit-1 | Drilling | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4451400% | 12.00 PM | 4451400% | 12.50 PM | Site clean
2 | 0717 | Drilling work for plateform installation | General Area | Bakkar | Project Team | Bakkar | Bakkar | Soliman-Admin | Unit-1 | Drilling | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4451500% | 12.40 PM | 4451500% | 4.00 PM | Site clean
3 | 0719 | Photo sensor fixxing work in project room middle point | General Area | Zahirul | Cosmic | Azim-HSE | Bakkar | Zahirul-Project | Unit-1 | cable connection | General Work | Safety Shoe, Helmet, mask, hand gloves | Biplob | Biplob | yellow-H-055 & Black-144 | 4451500% | 4.15 PM | 4451500% | 7.00 PM | Site clean
4 | 0721 | Vessel fill with stone & pvc pipe line connection work | General Area | Bakkar | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-1 | Pipe line connection work | General Work | Safety Shoe, Helmet, mask, hand gloves | N/A | N/A | N/A | 4451600% | 10.00PM | 4451600% | 5.00 PM | Site clean
5 | 0720 | W/H Aisle master Hydralic pipe open & fixing work | General Area | Bakkar | Jahangir Mechanical work | Bakkar | Bakkar | Md.Kaisar - W/H | Unit-3 | Pipe replace | General Work | Safety Shoe, Helmet, mask, hand gloves | Bakkar | Bakkar | aisle master key | 4451600% | 6.00 PM | 4451600% | 6.00 PM | Site clean
6 | 0725 | CO2 Sounder fixxing work | General Area | Zahirul | DCS | Zahirul | Zahirul | Pijush-Admin | Unit-1 | Drilling | General Work | Safety Shoe,safe glass Helmet, mask, hand gloves | N/A | N/A | N/A | 4451700% | 11.30 AM | 4451700% | 5.30 PM | Site clean
7 | 0729 | Admin Store Electrical Connection | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kamal-Admin | Unit-1 | Electrical Connectiom | General Work | Safety Shoe, Helmet,, mask, hand gloves | N/A | N/A | N/A | 4451900% | 9.00 AM | 4451900% | 4.00 PM | Site clean
8 | 0726 | Co2 Electrical Connection | General Area | Project | DCS | Bakkar | Bakkar | Pijush-Admin | Unit-1 | Electrical Connectiom | General Work | Safety Shoe, Helmet, mask, hand gloves | N/A | N/A | N/A | 4451800% | 11.00 am | 4451800% | 2.00 PM | Site clean
9 | 0727 | Technical room Painting Work | General Area | Project | Vision Engineering | Bakkar | Bakkar | Jahangir-Technical | Unit-1 | Wall Painting | General Work | Safety Shoe, Helmet, mask, hand gloves,face visor | N/A | N/A | N/A | 4451900% | 9.00AM | 4451900% | 6.30 PM | Site clean
10 | 0728 | Unit-3 5th Floor sample room paintig work | General Area | Project | Vision Engineering | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Wall Painting | General Work | Safety Shoe, Helmet, mask, hand gloves,face visor | N/A | N/A | N/A | 4451900% | 9.00 AM | 4451900% | 6.30 PM | Site clean
11 | 0732 | Unit-3 5th Floor sample room paintig work | General Area | Project | Vision Engineering | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Wall Painting | General Work | Safety Shoe, Helmet, mask, hand gloves,face visor | N/A | N/A | N/A | 4452100% | 9.00 PM | 4452100% | 6.00 PM | Site clean
12 | 0733 | Rain water drainage line hole & Pvc pipe line work | General Area | Project | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-1 | Drilling | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4452100% | 9.30 PM | 4452100% | 4.30 PM | Site clean
13 | 0736 | Unit-3 1st floor IT room electrical socket fixinfg work | General Area | Project | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Electrical Connection | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | Faruk | Faruk | Yellow-H-55 | 4452200% | 10.00AM | 4452200% | 11.00 AM | Site clean
14 | 0742 | Unit-3 3rd Floor AC no-2 Leakge check & Gas flling Work | General Area | MTC | Popular Electronics | Omar Faruk-k-Mtc | Bakkar | Pranab- U3 | Unit-3 | Gas Filling | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | Faruk | Faruk | Yellow-70 & black-h-144 | 4452400% | 11.10 AM | 4452400% | 7.40 Pm | Site clean
15 | 0741 | sitkiny Fixing C-Tack Plant Door | Red Zone | Project | Vision Engineering | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Drilling | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4452400% | 9.00AM | 4452400% | 3.00 PM | Site clean
16 | 0739 | Unit-3 3rd Floor AC no-2 Leakge check & Gas flling Work | General Area | Project | Popular Electronics | Omar Faruk-k-Mtc | Bakkar | Pranab- U3 | Unit-3 | Gas Filling | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | Faruk | Faruk | Yellow-H-71 & Back -H 144 | 4452300% | 2.30 PM | 4452300% | 4.30 PM | Site clean
17 | 0744 | unit-3 Top Floor Driking Water DB fixing Work | Red Zone | Project | Aquafit | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Drilling Work | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4452400% | 11.15 AM | 4452400% | 7.00 PM | Site clean
18 | 0749 | Unit -3 Top floor drinking Water motor fixed work & cable dressing | General Area | Project | Aquafit | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Drilling Work | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4452500% | 1.30 PM | 4452500% | 4.50 Pm | Site clean
19 | 0745 | New singeing Modificaton work | Red Zone | Project | Afrin Eng. Works | Bakkar | Bakkar | Imran-MTC | Unit-1 | cutting ,Drilling ,Welding | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4452500% | 10.30 PM | 4452500% | 6.00 PM | Site clean
20 | 0750 | Pvc Channel fixing & Co2 AC line connection work | General Area | Project | Project Team | Bakkar | Bakkar | Imran-MTC | Unit-1 | Drilling | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4452600% | 9.00 AM | 4452500% | 7.00 Pm | Site clean
21 | 0511 | Unit -1 IT Room AC line Socket Fixing work (Co2 control box ) | General Area | MTC | Project Team | Dulal | Dulal | Saiful -Admin | Unit-1 | Electrical Connection | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | Faruk | Faruk | yellow -077 | 4452700% | 10.30 AM | 4452700% | 01.00 Pm | Site clean
22 | 0516 | C tack Door lock Work adjustment | General Area | Bakkar | Vision Engineering | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Drilling Work | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4452900% | 11.00 AM | 4452900% | 11.20 AM | Site clean
23 | 0517 | Unit-1st Floor IT Room | General Area | Bakkar | Mars Build | Bakkar | Bakkar | Pranab- U3 | Unit-1 | Side cover Fixed | General Work | Safety Shoe, Helmet, mask, hand gloves | N/A | N/A | N/A | 4452900% | 12.00 PM | 4452900% | 12.45 PM | Site clean
24 | 0518 | Table box lock fixing Work | General Area | MTC | Mars Build | Bakkar | Bakkar | Arup-Project | Unit-1 | Lock Fixing Work | General Work | Safety Shoe, Helmet, welding glass, mask, hand gloves | N/A | N/A | N/A | 4452900% | 6.00 Pm | 4452900% | 6.00 PM | Site clean
25 | 0519 | Unit -3 Top floor drinking trey fixxing & cable dressing | Red Zone | Bakkar | Project Team | Bakkar | Bakkar | Kamal-Admin | Unit-3 | Drilling Work | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4452900% | 2.30PM | 4452900% | 6.00 Pm | Site clean
26 | 0526 | Unit-3 Infront security room Electrical DB Install | General Area | Bakkar | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-3 | Cable Dressing Work | General Work | Safety Shoe, Helmet, safety glass, mask, hand gloves | N/A | N/A | N/A | 4450200% | 10.00 AM | 4453200% | 4.00Pm | Site clean
27 | 0443 | NMP floor apoxy work | General Area | Mahfuz | Nerolack | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | floor casting work | General Work | safety glass,mask,handgloves,safety shoe | N/A | N/A | N/A | 4450100% | 8.30 AM | 4450100% | 5.00PM | Site clean
28 | 0804 | Dry chain oven(plate form,support ,sliding ralling work ) | Red Zone | Mahfuz | Mars Build | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | cutting ,Drilling ,Welding | Work at Height | Helmet,safety shoe,Safety glass,mask,face visor | Faruk | Faruk | yellow-52 | 4450100% | 10.30 Am | 4450100% | 5.00 PM | Site clean
29 | 0806 | Chain oven( electrical wiring work ) | Red Zone | samim | Vision Engineering | Azim-HSE | Shamim | Samim-Project | Unit-2 | cable wiring work | Work at Height | Helemt,Safety glass,mask,hand glubs,safety shoe | HSE | HSE | yellow-082 | 4450200% | 11.00 AM | 4450200% | 5.00PM | Site clean
30 | 0805 | Chain Oven (Plat Form Extension Work ) | Red Zone | samim | Mars Build | Azim-HSE | Shamim | Samim-Project | Unit-2 | cutting ,Drilling ,Welding | Work at Height | Helemt,safet yglass,mask,hand glubs,safety shoe | HSE | HSE | yellow-082 | 4450200% | 10.35AM | 4450200% | 5.30Pm | Site clean
31 | 0812 | Chain oven(acrylic sheet channel & Painting work) | General Area | samim | Mars Build | Imran-Hse | Shamim | Samim-Project | Unit-2 | cutting ,Drilling ,Welding | General Work | Helmet,face visor,Safety Glass,mask,hand glubs,safety shoe,body Aprone | N/A | N/A | N/A | 4450300% | 9.40AM | 4450300% | 6.00Pm | Site clean
32 | 0815 | Chain oven(cbale tray making & socket fixing& cable dressing | Red Zone | samim | Vision Engineering | Imran-Hse | Shamim | Samim-Project | Unit-2 | Driling,cable dressing | General Work | Helmet,face visor,Safety Glass,mask,hand glubs,safety shoe,body Aprone | N/A | N/A | N/A | 4450300% | 10.00AM | 4450300% | 5.00PM | Site clean
33 | 0809 | Chain oven(cable tray,light,fan install& pipe cutting work) | Red Zone | Mahfuz | Vision Engineering | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | cable dressing&drilling cutting | Work at Height | Helmet,face visor,Safety Glass,mask,hand glubs,safety shoe,safety belt | Azim-HSE | Azim-HSE | Yellow-68,red-03 | 4450400% | 8.50 AM | 4450400% | 5.00 Pm | Site clean
34 | 0825 | Mixxing Room Painting work | General Area | Mahfuz | Vision Engineering | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Wall painting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4450500% | 8.40 AM | 4450500% | 5.00Pm | Site clean
35 | 0828 | Chain Oven walldismalting,painting,tray fixing,cable dressing | Red Zone | Mahfuz | Mars build & Vision Engineering | Osman | Mahfuz | Mahfuz-Project | Unit-2 | dismalting,cable dressing,tray making work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,yar plug | N/A | N/A | N/A | 4450500% | 9.00 AM | 4450500% | 1.00 PM | Site clean
36 | 0406 | Ralling,ductline making,grinding,material handeling work | Red Zone | Mahfuz | Mars Build & Jinnat Ali | Azim-HSE | Mahfuz | Azim-HSE | Unit-2 | Driling,cable dressing, grinding welding | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,yar plug | N/A | N/A | N/A | 4450500% | 8.40 AM | 4450500% | 5.00PM | Site clean
37 | 0812 | Chain Oven cable dressing,eiring,light,fan,fixing,drilling | General Area | Mahfuz | Vision Engineering | Osam-HSE | Mahfuz | Mahfuz-Project | Unit-2 | drilling & cable dressing work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,yar plug | N/A | N/A | N/A | 4450600% | 9.30AM | 4450600% | 5.00Pm | Site clean
38 | 0811 | NMP CCTV fixing,&terpalin fixing workm,angle cutting,welding | Red Zone | Mahfuz | Mars Build | Osman-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Driling & CCtv Fixing Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | N/A | N/A | N/A | 4450600% | 9.00AM | 4450600% | 5.00PM | Site clean
39 | 0843 | Sub-Station(Call point installation by drilling ) | General Area | Mahfuz | DCS | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | wall Drilling Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4450800% | 9.25 | 4450800% | 5.00Pm | Site clean
40 | 0913 | NMP wall painting & rubber mat transfer work | General Area | Mahfuz | Vision Engineering | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Wall painting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4451200% | 8.40AM | 4451200% | 5.00PM | Site clean
41 | 0918 | Chain Oven MCP Manual call point shifting | General Area | samim | Project Team | Azim-HSE | Shamim | Samim-Project | Unit-2 | Wall driling work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4451300% | 1.00Pm | 4451300% | 5.00PM | Site clean
42 | 0817 | Unit- 2 Rooftop Leakage repair work | General Area | Mahfuz | Project Team | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Leakage Repair Work | Work at Height | Helmet,Safety shoe ,hand glubs | N/A | N/A | N/A | 4451300% | 2.30PM | 4451300% | 5.00PM | Site clean
43 | 0821 | Methanol Store plastar remiving&casting work)scafolding moving | General Area | Mahfuz | Globe enterprise | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Plastar repair work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | N/A | N/A | N/A | 4451500% | 9.00 AM | 4451300% | 5.00PM | Site clean
44 | 0825 | Unit-2 pocket gate (cutting,Grinding&Repair Work) | General Area | Mahfuz | Mars Build | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | cutting ,Drilling ,Welding | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4451700% | 9.00 AM | 4451700% | 5.00 PM | Site clean
45 | 0827 | U-2 Railing making,installation,Gate makiing work | General Area | Mahfuz | Mars Build | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | cutting ,Drilling ,Welding | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4451800% | 9.00 AM | 4451700% | 5.00PM | Site clean
46 | 0829 | NAP(Mixing Room)painting & Rubber Mat removing floor grinding | General Area | Mahfuz | Vision Engineering | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | wall Painting Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4451900% | 8.50AM | 4451900% | 5.00PM | Site clean
47 | 0828 | Main Gate door & Railing Painting Work | General Area | Mahfuz | Mars Build | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Painting Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4451900% | 9.00AM | 4451900% | 5.00pm | Site clean
48 | 0107 | Chain Oven Railing fixxing & plant modification | Red Zone | Mahfuz | Zinnat Ali Enterprise | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | driling& Grinding Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,aprone | Faruk | Faruk | y-82 R-02 B-146 | 4451900% | 9.00AM | 4451900% | 5.00PM | Site clean
49 | 0101 | Ramp Making Work | General Area | samim | Mars Build | Imran-Hse | Shamim | Samim-Project | Unit-2 | cutting & welding Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,aprone | N/A | N/A | N/A | 4451900% | 9.00AM | 4451900% | 5.00PM` | Site clean
50 | 0106 | Chain Oven Support Fixing,support Making,Railing Fixxing | Red Zone | samim | Zinnat Ali Enterprise | Imran-Hse | Shamim | Samim-Project | Unit-2 | cutting & welding Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452000% | 9.00AM | 4452000% | 5.00PM | Site clean
51 | 1017 | Chain Oven DB(hole,driling,cable wiring,switch install work ) | Red Zone | Samim | Project Team | Osman-HSE | Shamim | Samim-Project | Unit-2 | drilling work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452000% | 12.00PM | 4452000% | 5.00PM | Site clean
52 | 1016 | U-2 Back gate(gate&railing Painting&wall painting Work | General Area | Mahfuz | Mars Build | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Painting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452000% | 11.20AM | 4452000% | 5.00PM | Site clean
53 | 1030 | Stitching Auto turning M/C connection | General Area | Mahfuz | Project Team | Imran-Hse | Mahfuz | Farhad-U2 | Unit-2 | Drilling work | General Work | Helmet,mask,hand glubs,safety shoe | Faruk | Faruk | yellow-61,red-02 | 4452200% | 9.15AM | 4452200% | 5.00PM | Site clean
54 | 0106 | U-2 Back side Sunshade top(brick Wall Making ) | General Area | Mahfuz | Mars Build | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Wall ready Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452200% | 9.15AM | 4452200% | 5.00PM | Site clean
55 | 0129 | U-2 Mixing(rod cutting,Compaction,brick wall Making) | General Area | Mahfuz | Mars Build | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | walll making work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452200% | 8.45AM | 4452200% | 5.00PM | Site clean
56 | 0836 | Methanol Storage(scafolding install,MS pipe install,material shifting | Red Zone | Mahfuz | DCS | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Ms pipe cutting &cutting Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452400% | 9.00AM | 4452400% | 5.00PM | Site clean
57 | 0837 | Methanol Storage(scafolding install,MS pipe install,material shifting | Red Zone | Mahfuz | DCS | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Ms pipe cutting &cutting Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452500% | 9.00AM | 4452500% | 5.00PM | Site clean
58 | 1113 | NMP(Water line Fixing in leaching Tank) | General Area | samim | Project Team | sahidul-HSE | Shamim | Samim-Project | Unit-2 | G.I pipe fixxing work | General Work | Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452600% | 8.30PM | 4452600% | 5.00PM | Site clean
59 | 0840 | Methanol Store(Pipe line extended Work) | Red Zone | Mahfuz | DCS | sahidul-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Cutting & drilling work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452600% | 8.45AM | 4452600% | 5.00pm | Site clean
60 | 0845 | Methanol store(Pipe&support cutting&making&smoke detection install work | Red Zone | Mahfuz | DCS | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Cutting &making Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452700% | 8.50AM | 4452700% | 5.00PM | Site clean
61 | 0842 | Methanol Storage(MS pipe installaion Work ) | Red Zone | Mahfuz | DCS | Azim-HSE | Mahfuz | Mahfuz-Project | Unit-2 | Pipe Installatiuon Wrok | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | N/A | N/A | N/A | 4452700% | 8.30AM | 4452700% | 5.00PM | Site clean
62 | 0843 | Methanol store(Pipe&Tie cutting&fixing,support making,material shifting. | Red Zone | samim | DCS | Imran-Hse | Shamim | Samim-Project | Unit-2 | Pipe Cutting & fixxing Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visore,aprone,belt | N/A | N/A | N/A | 4452800% | 8.45AM | 4452800% | 5.00PM | Site clean
63 | 0431 | Chain oven&NMP(Railing Installaion,Platform extention&support Fixxing | General Area | samim | Mars Build | Imran-Hse | Shamim | Samim-Project | Unit-2 | Grinding& Material Shifting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,body Aprone | N/A | N/A | N/A | 4452900% | 9.00AM< | 4452900% | 5.00PM | Site clean
64 | 0436 | NMP Platform Extension,Supprort Fixxing,railing installaion Work | Red Zone | samim | Mars Build | Azim-HSE | Shamim | Samim-Project | Unit-2 | Grinding& Material Shifting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4452900% | 9.00AM | 4452900% | 5.00PM | Site clean
65 | 0846 | Methanol Store(Pipe Tread Cutting,support,fixxing smoke detectiom install | Red Zone | Mahfuz | DCS | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | Cutting &making Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,safety belt | N/A | N/A | N/A | 4453000% | 8.30AM | 4453000% | 5.00PM | Site clean
66 | 0435 | Floor Apoxy & cleaning Work | General Area | Mahfuz | Nerolack | Imran-Hse | Mahfuz | Mahfuz-Project | Unit-2 | floor casting work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4453000% | 8.30 AM | 4453000% | 5.00PM | Site clean
67 | 0526 | unit-3 infront security room DB Install&rod cutting work,cable dressing | General Area | Bakkar | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-3 | db Installation&rodcutting work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | Faruk | Faruk | Y-h053,B-H142 | 4453200% | 10.00AM | 4453200% | 5.00PM | Site Clean
68 | 0528 | Unit-3 infront security room Pvc loine making &Vessel clean work | General Area | Bakkar | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-3 | pvc pipe install work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | N/A | N/A | N/A | 4453300% | 10.Am | 4453300% | 4.00PM | Site Clean
69 | 0532 | Project Room door stoper fixing Work | General Area | Bakkar | Project Team | Bakkar | Bakkar | Zahirul-Project | Unit-1 | Drilling Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4453600% | 4.30Pm | 4453600% | 5.10PM | Site Clean
70 | 531 | Infront Security Room Rain Water plant DB&shade Fixxing Work | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kamal-Admin | Unit-1 | Db Fixing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4453600% | 10.45AM | 4453600% | 6.00PM | Site Clean
71 | 0535 | Infront Security Room Rain Water plant DB&Flow meter Fixing work | General Area | Bakkar | Smart Water | Bakkar | Bakkar | Kamal-Admin | Unit-1 | Flow Meter Fixxing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4453700% | 11.40AM | 4453700% | 6.00PM | Site Clean
72 | 0536 | Unit-3 Roof top (DM water plant Electrical socket fixing work) | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kamal-Admin | Unit-3 | Socket Fixing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4453800% | 12.20AM | 4453800% | 4.00PM | Site Clean
73 | 0537 | Unit-3 infront security room(DM plant aluminium channel fixng | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kamal-Admin | Unit-3 | Drilling Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4453800% | 8.30Am | 4453800% | 4.00PM | Site Clean
74 | 0541 | Unit-3 Office Ground floor KW meter setup work | General Area | Bakkar | Project Team | Bakkar | Bakkar | Helal-Admin | Unit-3 | wall drilling work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | Faruk | Faruk | Yellow-H055 | 4454000% | 9.30AM | 4454000% | 7.00PM | Site Clean
75 | 0309 | IT&subStation Room solinaid valve connection Work | General Area | Bakkar | DCS | Bakkar | Bakkar | Pijush-Admin | Unit-1 | Electrical Connection Work | General Work | Helmet,,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4454900% | 11.00AM | 4454900% | 3.30PM | Site Clean
76 | 0310 | PVC-2 Side A Singeing Area New DB fixing Work | Red Zone | Bakkar | Project Team | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Db Fixxing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe, | N/A | N/A | N/A | 4455000% | 9.30AM | 4455000% | 6.00PM | Site Clean
77 | 0312Y | New singeing Body Fixxing work | Red Zone | Bakkar | Project Team | Bakkar | Bakkar | Koushik-U1 | Unit-1 | singeing body Installation Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | Ali,Faruk,Kaisar | Ali, Faruk | y-055,053R-020,021,016,014 | 4455200% | 9.15AM | 4455200% | 3.00PM | Site Clean
78 | 0613 | Pvc-2 New singeing area cable&channel Insatallation Work | Red Zone | Bakkar | Project Team | Bakkar | Bakkar | Koushik-U1 | Unit-1 | aluminium channel fixing | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor | Faruk | Faruk | Yellow-h053 | 4455300% | 10.30AM | 4455300% | 5.45PM | Site Clean
79 | 0848 | Methanol Storage(MS pipe install,drilling,cutting,grinding,paint work) | Red Zone | Mahfuz | DCS | Azim-HSE | Mahfuz | Azim-HSE | Unit-2 | cutting,drillinf&Paint Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4453100% | 8.40AM | 4453100% | 5.00PM | Site Clean
80 | 0849 | Methanol Storage(MS pipe install,drilling,cutting,grinding,paint work) | Red Zone | Mahfuz | DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | cutting,drillinf&Paint Work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4453200% | 8.40AM | 4453200% | 5.00Pm | Site Clean
81 | 0307 | Mixxing Room(Painting Work) | General Area | Mahfuz | Vision Engineering | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Wall Paint work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4453300% | 9.30AM | 4453300% | 5.00PM | Site Clean
82 | 1608 | Plying out side(Ms pipe line &pipe cutting& joint Work) | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | cutting& Fitting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4453400% | 9.30AM | 4453400% | 5.00PM | Site Clean
83 | 1616 | Mixxing Room Weight Scale M/C chech & repair work | General Area | Mahfuz | SS Weighing solution | Azim-HSE | Shamim | Mizan-Technical | Unit-2 | scale repair | General Work | mask,Handglubs,safety shoe | N/A | N/A | N/A | 4453500% | 11.00AM | 4453500% | 3.00PM | Site Clean
84 | 1609 | Out Side of Flying(MS Pipe line work) | General Area | Samim | DCS | Samim | Shamim | Samim-Project | Unit-2 | pipe line work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4453500% | 9.00AM | 4453500% | 5.00PM | Site Clean
85 | 1623 | Infront Methanol Storage (MS pipe re-location) | General Area | Mahfuz | Project Team | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | RE-Location work | General Work | Helmet,Hand glubs,safety shoe | N/A | N/A | N/A | 4453700% | 9.00AM | 4453700% | 5.00PM | Site Clean
86 | 0837 | NMP/Chain Oven(curtain fix,exaust fan install,cable dressing,tray fix) | Red Zone | Samim | Mars build & Vision Engineering | Imran-HSE | Shamim | Samim-Project | Unit-2 | drilling ,cutting,cable connection work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | Faruk | Faruk | Y-84,b-02 | 4453700% | 8.45AM | 4453700% | 1.00PM | Site Clean
87 | 1630 | Out Side of Flying(MS Pipe line &Excavation work) | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Excavation Work | General Work | Helmet,Safety Glass,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4453800% | 9.30AM | 4453800% | 5.00PM | Site Clean
88 | 1636 | Out side Flying (MS pipe line,Cutting,grinding,welding,Excavation) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | drilling work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4453900% | 5.50AM | 4453900% | 5.00PM | Site Clean
89 | 1644 | Sub Station out side /Methanol storage(Co2 cylinder installation work) | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Shawkat-MTC | Unit-2 | installation work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454000% | 9.00AM | 4454000% | 5.00PM | Site Clean
90 | 1705 | NAP-A(Foam Tank&methanol Tank Shifting) | General Area | Mahfuz | Project Team | Mahfuz | Mahfuz | Saju-Technical | Unit-2 | material shifting work | General Work | Helmet,Hand glubs,safety shoe | N/A | N/A | N/A | 4454100% | 5.00PM | 4454100% | 9.00PM | Site Clean
91 | 1650 | Beside Methanol storage(exavation,brick wall,ms pipe line work) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Wall making | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4454200% | 8.30AM | 4454200% | 5.00PM | Site Clean
92 | 1715 | Beside Methanol storage(exavation,brick wall,ms pipe line work) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Wall making | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454300% | 8.45AM | 4454200% | 5.00PM | Site Clean
93 | 1716 | Unit-2 fork lift repair Work | General Area | Bakkar | Jahangir Mechanical work | Mahfuz | Bakkar | kamal-WH | Unit-2 | clutch open work | General Work | Hand glubs ,Safety shoe | N/A | N/A | N/A | 4454300% | 10.45AM | 4454300% | 5.00PM | Site Clean
94 | 1726 | Beside Methanol&NMP Exavation,brick wall,MS Pipe Shifting | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Brick Wall making work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454400% | 8.30AM | 4454400% | 5.00PM | Site Clean
95 | 1727 | Sub-Station (gland fixxing&Cylinder electrical Connetion work) | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Shawkat-MTC | Unit-2 | Electrical Connection Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4454400% | 10.45AM | 4454400% | 5.00PM | Site Clean
96 | 1733 | Beside Methanol storage(RCC casting,shuttering Painting,base plare fixed) | General Area | Mahfuz | BBSL&Vision | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | RCC casting Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454700% | 8.45AM | 4454700% | 5.00PM | Site Clean
97 | 0112 | NMP&Sub-Station(angle support,MS Pipe line installation,Material shifting) | Red Zone | Mahfuz | DCS | Mahfuz | Mahfuz | Shawkat-MTC | Unit-2 | angle support Fixxing work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4454700% | 8.45AM | 4454700% | 5.00PM | Site Clean
98 | 1735 | Beside Methanol Storage(column install,brick wall making,msPipe line work) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | column Install work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454800% | 8.30AM | 4454800% | 5.00PM | Site Clean
99 | 1737 | Dry Chain oven(Support Welding Work) | Red Zone | Samim | Project Team | Samim | Shamim | Sohan-U2 | Unit-2 | support fixxing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454800% | 9.00AM | 4454800% | 5.00Pm | Site Clean
100 | 1743 | Beside Methanol store(Column install,brick wall making,,plastering,pipe line fabrication | General Area | Samim | BBSL&DCS | Samim | Shamim | Samim-Project | Unit-2 | wall making & pipe fabrication work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4454900% | 8.30AM | 4454900% | 6.00PM | Site Clean
101 | 1802 | Sub-station(Cbale fulling,Breakar fixxing,cylider electrical power connection) | General Area | Mahfuz | Project Team | Mahfuz | Mahfuz | Shawkat-MTC | Unit-2 | cable connectio work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | Faruk | Faruk | yellow-086 | 4455000% | 2.45 PM | 4455000% | 5.00PM | Site Clean
102 | 0109 | Beside Methanol store(Column install,brick wall making,,plastering,pipe line fabrication | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Mahfuz-Project | Unit-2 | Cable &Brick Wall making work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4455000% | 8.30AM | 4455000% | 5.00PM | Site Clean
103 | 0111 | Beside methanol/sub station(Angle welding,wall sheeting cable fulling,co2 comitioning, | Red Zone | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Shawkat-MTC | Unit-2 | Cable &Brick Wall making work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone | N/A | N/A | N/A | 4455100% | 8.30AM | 4455100% | 5.00PM | Site Clean
104 | 1812 | Chain oven(Exaust Fanmotor pully belt opening,checking,fitting) | General Area | Samim | Project Team | Samim | Shamim | Sohan-U2 | Unit-2 | Exaust Fan checking | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | Imran-HSE | Imran-HSE | yellow-61,Red-02 | 4455200% | 4.00PM | 4455200% | 6.30PM | Site Clean
105 | 0117 | NMP out side methanol Storage,Sub-Station(MS pipe line work,Wall clading,co2 electrical connetion jerking M/C relocation) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Saju-Technical | Unit-2 | drilling,re-location work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | Faruk | faruk | yellow-61 | 4455200% | 8.30AM | 4455200% | 5.00PM | Site Clean
106 | 1819 | Packing &workshop(auto O/L safety guard opening,Guard making& guard fixing) | General Area | Samim | Project Team | Samim | Shamim | Kazi-Packing | Unit-2 | Guard fixxing work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | Imran-HSE | Imran-HSE | yellow-60,red-02 | 4455300% | 11.10AM | 4455300% | 5.00PM | Site Clean
107 | 0118 | NMP Out side methanol Area (MS pipe line install area &house keeping) | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Aziz-U2 | Unit-2 | pipe line work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4455300% | 8.45AM | 4455300% | 5.00pm | Site Clean
108 | 1824 | sub-station&compressor room(Breakar installation Work&connection) | General Area | Samim | Project Team | Samim | Shamim | Shawkat-MTC | Unit-2 | breakar connect work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | Faruk | Faruk | yellow-42 | 4455400% | 8.50AM | 4455400% | 5.00PM | Site Clean
109 | 0119 | NMP Foam suptression (Pipe install,tie rod support,drilling,welding,grinding work ) | Red Zone | Samim | DCS&PN | Samim | Shamim | Samim-Project | Unit-2 | grinding,welding,drilling work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4455400% | 9.00AM | 4455400% | 6.30PM | Site Clean
110 | 0122 | NMP Foam suppression both side (Pipe install,tie rod support,drilling,welding,gringing work scafolding fixing work) | Red Zone | Raihan | DCS | Raihan | Zahirul | Mehedi-U2 | Unit-2 | grinding,welding,drilling work | Work at Height | Helmet,Safety Glass,mask,hand glubs,safety shoe,Face visor,aprone,safety belt | N/A | N/A | N/A | 4455600% | 8.30AM | 4455600% | 8.00PM | Site Clean
111 | 1846 | Chain oven(Coolin Fan belt Changing work) | General Area | Samim | Project Team | Samim | Shamim | Aziz-U2 | Unit-2 | belt fixing | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4455800% | 3.30PM | 4455800% | 8.30PM | Site Clean
112 | 1844 | Assembly Point & methanol storage back side(Floor chipping,Foam suppression moving work ) | General Area | Samim | DCS | Samim | Shamim | Samim-Project | Unit-2 | floor chipping | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4455800% | 9.30AM | 4455800% | 5.00PM | Site Clean
113 | 0320 | Unit-3 1st floor (new auto overlock install,interlock setup&safety guard fixxing) | Red Zone | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | installation work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | faruk | Faruk | yellow-h-55 | 4455700% | 9.15AM | 4455700% | 5.50PM | Site Clean
114 | 0327 | W/h Aisle master hydralic pipe open work | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kaiser-WH | Unit-3 | pipe open work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4456100% | 11.00PM | 4456100% | 12.00PM | Site Clean
115 | 0326 | IT Room & sub Station mk box fixing work | General Area | Bakkar | DCS | Bakkar | Bakkar | Forkan-Admin | Unit-3 | box fixxing Work | General Work | Helmet,Safety Glass,mask,hand glubs,safety shoe | N/A | N/A | N/A | 4456100% | 10.30AM | 4456100% | 3.00PM | Site Clean
116 | 0128 | Foam Tank installation, MS Pipe line, Floor Chiping & Finishing work at Unit-02 | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Shazed-U2 | Unit-2 | installation work | General Work | Helmet,Face Visor,Safety goggles,Mask,Hand Gloves,Safety shoe, Apron,Safety belt | N/A | N/A | N/A | 4455800% | 8.30AM | 4455800% | 7.00PM | Site Clean
117 | 1916 | Socket installation work at unit-02 packing | General Area | Mahfuz | Project Team | Mahfuz | Mahfuz | Shazed-U2 | Unit-2 | Installation work | General Work | Helmet,Safety goggles,Mask,Hand gloves,Safet shoe | Faruk | Faruk | Yellow-61 | 4456000% | 2.00PM | 4456000% | 7.00PM | Site Clean
118 | 0129 | Brick wall making,Sheet&Angle fitting & MS pipe line installation work for Foam | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Farhad-U2 | Unit-2 | Sheet fitting, fixing & Pipe Installation work | Work at Height | Helmet,Face Visor,Safety goggles,Mask,Hand Gloves,Safety shoe, Apron,Safety belt | N/A | N/A | N/A | 4456000% | 8.30AM | 4456000% | 7.00PM | Site Clean
119 | 1917 | Profile modification,tank shfting & former alignment | General Area | Shamim | Project Team | Samim | Shamim | Samim-Project | Unit-2 | Modification & Shifting work | General Work | Helmet,Mask,Hand gloves,Safet shoe | N/A | N/A | N/A | 4456100% | 8.30AM | 4456100% | 7.00PM | Site Clean
120 | 0615 | Aisle master hydraulic pipe replace work at warehouse-03 | General Area | Bakkar | Jahangir Mechanical work | Bakkar | Bakkar | Ashraf-WH | Unit-3 | Pipe replacement work | Work at Height | Helmet,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4456300% | 10.30 am | 4456300% | 01.00 pm | Site Clean
121 | 0332 | Weighing scale display checked at unit-03 warehouse | General Area | Bakkar | SS Weighing solution | Bakkar | Bakkar | Ashraf-WH | Unit-3 | Weighing Scale checking | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4456300% | 02.00 pm | 4456300% | 04.00 pm | Site Clean
122 | 0131 | Foam MS pipe installation & Angle fitting, Fixing work at unit-02 | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | kamal-WH | Unit-2 | Installation work | Work at Height | Helmet,Face visor,safety goggles,mask,hand gloves,safety shoe & apron | N/A | N/A | N/A | 4456300% | 08.30 am | 4456300% | 07.00 pm | 0132
123 | 1924 | Auto overlock machine safety guard installation work at unit-02 | Red Zone | Shamim | Project Team | Shamim | Shamim | Kazi-Packing | Unit-2 | Installation work | General Work | Helmet,hand gloves & safety shoe | Faruk | Faruk | Yellow & Red | 4456300% | 10.00 am | 4456300% | 06.30 pm | Site Clean
124 | 1930 | Floor repairing work & DB checking at unit-02 methanol storage | General Area | Mahfuz | Globe enterprise | Mahfuz | Mahfuz | kamal-WH | Unit-2 | Repairing work | General Work | Helmet,safety goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4456400% | 12.10 pm | 4456400% | 07.00 pm | Site Clean
125 | 0132 | Foam MS pipe installation, wall setting & Door fitting, Fixing work at unit-02 | General Area | Mahfuz | BBSL&DCS | Mahfuz | Mahfuz | Sohan-U2 | Unit-2 | Installation work | Work at Height | Helmet,Face visor,safety goggles,mask,hand gloves,safety shoe,apron & Apron | N/A | N/A | N/A | 4456400% | 08.30 am | 4456400% | 07.00 pm | 0131
126 | 1938 | Forklift wheel & wheel bearing servicing at warehouse-02 | General Area | Bakkar | MM Motors | Bakkar | Bakkar | kamal-WH | Unit-2 | Servicing work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4456500% | 02.30 pm | 4456500% | 04.00 pm | Site Clean
127 | 0133 | MS pipe fitting, welding, cutting, support making & materials shifting at unit-02 foam suppression shed. | General Area | Shamim | DCS | Shamim | Shamim | Samim-Project | Unit-2 | Pipe fittings & welding work | Work at Height | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4456500% | 09.00 am | 4456500% | 06.00 pm | Site Clean
128 | 0134 | Foam MS pipe installation work at unit-02 | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Sohan-U2 | Unit-2 | Pipe installation work | Work at Height | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4456600% | 09.00 am | 4456600% | 07.00 pm | 0134
129 | 0135 | Foam MS pipe installation, welding & cutting work at unit-02 | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Pipe installation work | Work at Height | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4456700% | 08.30 am | 4456700% | 05.00 pm | 0133
130 | 1207 | Floor grinding, floor painting, angle cutting & welding work at unit-02 | General Area | Shamim | Project Team | Shamim | Shamim | Samim-Project | Unit-2 | Floor repairng work | General Work | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe & apron | N/A | N/A | N/A | 4456800% | 08.30 am | 4456800% | 8.30 pm | 0134
131 | 0137 | MS pipe fitting, welding, cutting, support making & materials shifting at unit-02 foam suppression shed. | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Imran-HSE | Unit-2 | Pipe installation work | Work at Height | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4456800% | 08.30 am | 4456800% | 8.30 pm | 0135
132 | 0338 | Industrial socket installation at unit-03 5th floor & roof top. | General Area | Bakkar | Project Team | Bakkar | Bakkar | Kaiser-WH | Unit-3 | Installation work | General Work | Helmet,safety goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4456800% | 10.00 am | 4456800% | 05.00 pm | Site Clean
133 | 1209 | Railing, joint repair & angle cutting, welding work at unit-02 drying chain oven area | Red Zone | Mahfuz | Project Team | Mahfuz | Mahfuz | Sohan-U2 | Unit-2 | Repairing work | General Work | Helmet,face visor,safety goggles,mask,hand gloves,safety shoe & apron | N/A | N/A | N/A | 4456900% | 08.30 am | 4456900% | 8.30 pm | Site Clean
134 | 0340 | Industrial socket installation at unit-03 roof top. | General Area | Dulal | Project Team | Dulal | Dulal | Tamjid-U1&3 | Unit-3 | Installation work | General Work | Mask, Hand gloves & Safety shoe | Faruk | Faruk | Yellow | 4456900% | 12.00 pm | 4456900% | 03.00 pm | Site Clean
135 | 0344 | Capacitor change for DM water plant at Unit-03 roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Servicing work | General Work | Helmet,Mask,Hand gloves & safety shoe | Faruk | Faruk | Yellow | 4457000% | 12.00 pm | 4457000% | 12.15 pm | Site Clean
136 | 0343 | Solar panel unloading & shifting to unit-03 5th floor | General Area | Shamim | Project Team | Shamim | Shamim | Pranab- U3 | Unit-3 | Unloading work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457000% | 09.00 am | 4457000% | 06.15 pm | Site Clean
137 | 0635 | DM water plant motor checking at unit-03 roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Soliman-Admin | Unit-3 | Servicing work | General Work | Hand gloves & Safety shoe | Faruk | Faruk | Yellow | 4457100% | 05.40 pm | 4457100% | 06.55 pm | Site Clean
138 | 0348 | Solar panel shifting from Grand floor to unit-03 5th floor | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | Faruk | Faruk | Yellow | 4457100% | 08.45 am | 4457100% | 04.00 PM | Site Clean
139 | 0140 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | General Area | Mahfuz | DCS | Mahfuz | Mahfuz | Imran-HSE | Unit-2 | Installation work | General Work | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457100% | 08.30 am | 4457100% | 08.30 pm | 0137
140 | 0349 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457200% | 08.45 am | 4457200% | 07.00 pm | Site Clean
141 | 0141 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | Red Zone | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457200% | 09.30 am | 4457200% | 06.30 pm | Site Clean
142 | 0142 | Tarpauling fixing work at unit-02 | General Area | Shamim | Mars build | Shamim | Shamim | Samim-Project | Unit-2 | Fixing work | Work at Height | Helmet,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4457300% | 11.15 am | 4457300% | 05.00 pm | Site Clean
143 | 0350 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457300% | 08.45 am | 4457300% | 06.00 pm | Site Clean
144 | 0202 | Layout marking & floor chipping at unit-03 roof | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Construction work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457300% | 08.45 am | 4457300% | 05.00 pm | 0202
145 | 0205 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457400% | 08.45 am | 4457400% | 04.00 pm | Site Clean
146 | 0206 | Layout marking,floor drilling & slab top surface chipping at unit-03 roof | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Construction work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457400% | 08.30 am | 4457400% | 08.30 pm | 0206
147 | 0143 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | Red Zone | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457400% | 09.00 am | 4457400% | 06.00 pm | Site Clean
148 | 0210 | Slab making work at unit-01 | General Area | Bakkar | Mars build | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Civil work | General Work | Helmet,face visor,goggles,hand gloves & safety shoe | N/A | N/A | N/A | 4457500% | 08.45 am | 4457500% | 08.40 pm | Site Clean
149 | 0617 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457500% | 08.30 am | 4457500% | 08.40 pm | Site Clean
150 | 0213 | Slab chipping & rubbish remove | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Sayeed- Project | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457600% | 08.30 am | 4457600% | 08.30 pm | 206
151 | 1247 | Pipe cutting,welding,fitting for foam suppression work and goods replacing & measurement work. | Red Zone | Shamim | DCS | Shamim | Shamim | Sohan-U2 | Unit-2 | Installation work | General Work | Helmet,face visor,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457600% | 08.45 am | 4457600% | 06.00 pm | Site Clean
152 | 0214 | Roof slab top dismantling,chipping,drilling & rod cutting | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,face visor,goggles,mask,hand gloves,safety shoe & apron | N/A | N/A | N/A | 4457700% | 08.30 am | 4457700% | 08.30 pm | 0213
153 | 0216 | Washing area floor repair at unit-01 ground floor | General Area | Bakkar | Vision Engineering | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Civil work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4457700% | 11.15 am | 4457700% | 04.30 pm | Site Clean
154 | 0146 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457700% | 08.40 am | 4457700% | 05.30 pm | Site Clean
155 | 0219 | Slab top surface chipping & drilling | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457800% | 08.30 am | 4457800% | 08.30 pm | 0214
156 | 0147 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | General Area | Bakkar | DCS | Bakkar | Bakkar | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457800% | 10.00 am | 4457800% | 07.00 pm | Site Clean
157 | 0223 | Slab top surface chipping,drilling & DISMANTLING | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457900% | 08.30 am | 4457900% | 08.30 pm | 0219
158 | 0224 | Cable tray, water line & AC outdoor pipe relocation work | General Area | Bakkar | Vision Engineering | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Relocation work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | Dulal | Dulal | Yellow & Black | 4457900% | 08.45 am | 4457900% | 03.30 pm | Site Clean
159 | 2021 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | General Work | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4457900% | 09.45 am | 4457900% | 05.30 pm | Site Clean
160 | 2018Y | NFT plant modification work for custom visit | General Area | Shamim | Project Team | Shamim | Shamim | Sohan-U2 | Unit-2 | Modification work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4457900% | 06.30 am | 4457900% | 06.00 pm | Site Clean
161 | 0228 | Slab top surface dismantling & drilling | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458000% | 08.30 am | 4458000% | 08.30 pm | 0223
162 | 0215 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458000% | 08.45 am | 4458000% | 07.00 pm | 0617
163 | 0230 | Slab top surface dismantling & drilling | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458100% | 08.30 am | 4458100% | 08.30 pm | 0228
164 | 0149 | Foam pipe installation, support making, welding, cutting & grinding work at unit-02 | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458100% | 08.35 am | 4458100% | 06.00 pm | Site Clean
165 | 0150 | Foam pipe fitting,welding,leakage repair & gate valve installation work | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458200% | 09.15 am | 4458200% | 05.30 pm | Site Clean
166 | 0235 | Water pipe line & cable relocation and electric power cable connection | General Area | Mahfuz | Vision Engineering | Mahfuz | Mahfuz | Saiful-U3 | Unit-3 | Relocation work | Work at Height | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458200% | 08.30 am | 4458200% | 08.30 pm | 0228
167 | 0234 | Slab making work at unit-01 | General Area | Bakkar | Mars build | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Civil work | General Work | Helmet,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458200% | 08.45 am | 4458200% | 05.00 pm | Site Clean
168 | 0239 | Floor dismantling,drilling, CC casting & site cleaning on unit-03 roof | General Area | Sayeed | MBSL | Sayeed | Sayeed | Shahadat-Admin | Unit-1 | Civil work | General Work | Helmet,googles,hand gloves & safety shoe | N/A | N/A | N/A | 4458300% | 08.30 am | 4458300% | 06.00 pm | Site Clean
169 | 0236 | Drilling,base making, dismantling,rod cutting & setting work on unit-03 roof | General Area | Bakkar | MBSL | Bakkar | Bakkar | Saiful-U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458300% | 08.45 am | 4458300% | 07.00 pm | Site Clean
170 | 0241 | Water pipe line relocation work on unit-03 roof | General Area | Bakkar | Vision Engineering | Bakkar | Bakkar | Saiful-U3 | Unit-3 | Relocation work | General Work | Helmet,googles,hand gloves & safety shoe | N/A | N/A | N/A | 4458300% | 08.45 am | 4458300% | 07.00 pm | Site Clean
171 | 0243 | Drilling,base making, dismantling & rod cutting work on unit-03 roof | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458400% | 08.45 am | 4458400% | 07.00 pm | 0236
172 | 0244 | Floor cutting & drilling for soil test at unit-01 assembly point | General Area | Sayeed | Solidio | Sayeed | Sayeed | Koushik-U1 | Unit-1 | Civil work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458400% | 08.45 am | 4458400% | 04.40 pm | Site Clean
173 | 0312B | Underground waste water tank cleaning at unit-03 | General Area | Raihan | Talukdar | Raihan | Zahirul | Dabirul-Admin | Unit-3 | Cleaning work | Confined Space | Helmet,goggles,mask,hand gloves,safety shoe,safety belt & life line | Faruk | Faruk | N/A | 4458400% | 09.00 am | 4458400% | 09.00 am | Site Clean
174 | 2002 | Foam pipe fitting,welding,cutting,pipe lifting,support making & installation work | Red Zone | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458400% | 08.40 am | 4458400% | 06.00 pm | 2004
175 | 0246 | Drilling,rod fitting/fixing & apply epoxy on unit-03 roof | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | General Work | Helmet,face visor,goggles,mask,hand gloves,safety shoe & apron | N/A | N/A | N/A | 4458500% | 08.30 am | 4458500% | 08.30 pm | 0243
176 | 1309 | Forklift servicing at unit-02 | General Area | Bakkar | Navana | Bakkar | Bakkar | kamal-WH | Unit-2 | Servicing work | General Work | Mask & Hand gloves | N/A | N/A | N/A | 4458500% | 01.30 pm | 4458500% | 03.15 pm | Site Clean
177 | 0501 | Forklift servicing at unit-03 | General Area | Bakkar | Navana | Bakkar | Bakkar | Sarwar-WH | Unit-3 | Servicing work | General Work | Mask & Hand gloves | N/A | N/A | N/A | 4458500% | 03.30 pm | 4458500% | 06.00 pm | Site Clean
178 | 0247 | Solar panel shifting from unit-03 5th floor to roof top | General Area | Bakkar | Project Team | Bakkar | Bakkar | Pranab- U3 | Unit-3 | Shifting work | General Work | Helmet,hand gloves & safety shoe | N/A | N/A | N/A | 4458500% | 08.45 am | 4458500% | 06.00 pm | Site Clean
179 | 1402 | Floor casting at unit-01 assembly point | General Area | Bakkar | Solidio | Bakkar | Bakkar | Dabirul-Admin | Unit-1 | Civil work | General Work | Helmet,face visor,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458600% | 11.45 am | 4458600% | 04.00 pm | Site Clean
180 | 0622 | RCC dismantling,drilling,MS pipe shifting,Apply epoxy,Rebar installation,Rebar cutting & welding and painting work at unit-03 roof | General Area | Mahfuz | MBSL | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458600% | 08.00 am | 4458600% | 05.00 pm | Site Clean
181 | 0623 | Life line fitting & fixing,Scaffolding making & LPS tower installation | General Area | Mahfuz | Emkay | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Installation work | Work at Height | Helmet,goggles,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4458600% | 11.20 am | 4458600% | 05.00 pm | Site Clean
182 | 2004 | Chemical reffiling into cylinder,panel fitting,connection,pipe fitting,grinding,welding, material shifting & pneumatic pump opening | Red Zone | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458600% | 10.15 am | 4458600% | 06.00 pm | 2005
183 | 2005 | Foam pipe fitting,welding,cutting,pipe lifting,support making & installation work | Red Zone | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,visor,goggles,mask,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4458700% | 09.00 am | 4458700% | 06.00 pm | 2007
184 | 0316 | Underground waste water tank cleaning at unit-03 | General Area | Bakkar | Talukdar | Bakkar | Bakkar | Dabirul-Admin | Unit-3 | Cleaning work | Confined Space | Helmet,goggles,mask,hand gloves,safety shoe,safety belt & life line | Faruk | Faruk | Yellow | 4458700% | 09.00 am | 4458700% | 06.30 pm | Site Clean
185 | 0624 | Life line installation, down conductor fitting & fixing work on unit-03 roof | General Area | Mahfuz | Emkay | Mahfuz | Mahfuz | Pranab- U3 | Unit-3 | Installation work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4458700% | 08.30 am | 4458700% | 05.00 pm | 0623
186 | 0625 | Drilling,RCC dismantling,welding,painting,pipe lifting fixing,royal bolt fixing,MS rod,pipe welding & gas cutting | Red Zone | Raihan | MBSL | Raihan | Zahirul | Pranab- U3 | Unit-3 | Civil work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458700% | 08.00 am | 4458700% | 08.00 pm | 0622
187 | 0626 | Life line installation, down conductor fitting/fixing & installation work on unit-03 roof | Red Zone | Bakkar | Emkay | Bakkar | Bakkar | Dabirul-Admin | Unit-3 | Installation work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458800% | 08.00 am | 4458800% | 05.00 pm | 0624
188 | 0627 | Drilling,RCC dismantling,column rebar welding,apply epoxy,safety net & ms pipe installation,suttering & royal bolt fixing | Red Zone | Raihan | MBSL | Raihan | Zahirul | Zahirul-Project | Unit-3 | Civil work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458800% | 08.00 am | 4458800% | 05.00 pm | 0625
189 | 2007 | Foam filling into tank,panel commissioning, pipe fitting,support fitting & material shifting | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458800% | 08.35 am | 4458800% | 05.30 pm | 2008
190 | 2008 | Foam filling into tank,panel commissioning, pipe fitting,welding,support fitting & material shifting | General Area | Shamim | DCS | Shamim | Shamim | Imran-HSE | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458900% | 09.00 am | 4458900% | 05.30 pm | 2012
191 | 0628 | RCC dismantling,drilling,column rebar cutting & welding,safety net fitting & fixing,MS pipe installation & painting on unit-3 roof | Red Zone | Mahfuz | MBSL | Mahfuz | Mahfuz | Bakkar-Project | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458900% | 08.30 am | 4458900% | 07.00 pm | 0641
192 | 0629 | Life line installation,down condactor fitting & fixing on unit-03 roof | General Area | Mahfuz | Emkay | Mahfuz | Mahfuz | Bakkar-Project | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4458900% | 09.00 am | 4458900% | 03.00 pm | Site Clean
193 | 1438 | Male wash room painting & worker canteen tiles repair | General Area | Bakkar | Idea Eng. | Bakkar | Bakkar | Mahfuz-Project | Unit-3 | Repairing work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458900% | 08.45 am | 4458900% | 06.30 pm | Site Clean
194 | 1436 | MS pipe painting & C-tack floor repairing work at Unit-01 G/F | General Area | Bakkar | Mars build | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Repairing work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458900% | 08.45 am | 4458900% | 06.00 pm | Site Clean
195 | 1437 | Slab leveling work at unit-01 G/F | General Area | Bakkar | Idea Eng. | Bakkar | Bakkar | Koushik-U1 | Unit-1 | Repairing work | General Work | Helmet,goggles,mask,hand gloves & safety shoe | N/A | N/A | N/A | 4458900% | 08.45 am | 4458900% | 05.00 pm | Site Clean
196 | 0641 | RCC dismantling,drilling,column rebar cutting & welding,safety net fitting & fixing,MS pipe installation & painting on unit-3 roof | Red Zone | Mahfuz | MBSL | Mahfuz | Mahfuz | Bakkar-Project | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4459000% | 08.30 am | 4459000% | 07.00 pm | 0628
197 | 2012 | Foam panel commissioning,pipe fitting,welding,support making,material shifting & electric cable wiring | General Area | Shamim | DCS | Shamim | Shamim | Alvi-U2 | Unit-2 | Installation work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4459000% | 08.30 am | 4459000% | 06.30 pm | 2013
198 | 0630 | RCC dismantling,drilling,column rod welding,safety net fitting & fixing,painting & shuttering work on unit-3 roof | Red Zone | Raihan | MBSL | Raihan | Zahirul | Zahirul-Project | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | Faruk | Faruk | Yellow | 4459100% | 08.30 am | 4459100% | 05.00 pm | Site Clean
199 | 2018R | Copper bar fitting for LPS system at unit-02 NMP out side | General Area | Shamim | Emkay | Shamim | Shamim | Farhad-U2 | Unit-2 | Installation work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe & safety belt | N/A | N/A | N/A | 4459200% | 08.45 am | 4459200% | 01.00 pm | Site Clean
200 | 0642 | RCC dismantling,drilling,column rod welding,safety net fitting & fixing,painting & shuttering work on unit-3 roof | Red Zone | Raihan | MBSL | Raihan | Zahirul | Zahirul-Project | Unit-3 | Civil work | Work at Height | Helmet,face visor,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4459200% | 08.00 am | 4459200% | 04.50 pm | Site Clean
201 | 0646 | Water line pipe clump fixing work on unit-03 roof | General Area | Bakkar | Vision Engineering | Bakkar | Bakkar | Zahirul-Project | Unit-3 | Repairing work | Work at Height | Helmet,goggles,mask,hand gloves,safety shoe,apron & safety belt | N/A | N/A | N/A | 4459200% | 12.00 pm | 4459200% | 03.40 pm | Site Clean
[16 empty] | 4459300% |  | 4459300%